## Summary on-going
Digital
| Inisiatif | Status | Resource | PM
1 | Pending NTB
| a. M2U Schedule dan ATM Activation, PIC yang follow up siapakah? Dari Gabby sudah info link source | Pending SIT
| b. NTB: Pentest dari Play Store dan Apps Store | Pending upload to Play/ Apps Store
2 | Merged 3 SR include req email trx PLN | Pending nego | Penril, Bella | M
3 | Perbaikan NTB Web (OJK, Dukcapil, Incomplete, MBM Feedback) | SIT | Vendor Prima, Tomy, Rio | M
4 | Embos NTB ATM Card (CPC) | Dev | Gian, Wiwit | M
5 | Pembelian Travel Insurance (bancassurance) | SIT | Rio | N
6 | Penyesuaian TD Online | FSD Finalization | Rio
7 | Perbaikan ETB (included ST2A) | SR Finalization | Rio
8 | NTB - MBM Feedback | Quieuing dev | Rio
9 | NTB - MBM Feedback (Incomplete - impacted to DCIF) | Pending share req to Ebworx | Brian
10 | eMoney | Draft RFQ and POC doc shared by user for impacted apps review - architecture flow
CFS
| Inisiatif | Status | Resource
1 | DD: ESB Modernization, apakah bisa jalan duluan services terkait ESB
2 | BAOS | Re-FSD | Brian, Oki

## List Req eChannel
Priority | Target UAT Done | Target Date Publish Customer | Item | BRD Status | Status | Versi Aplikasi | Nama BRD | No SR | Req Type | In-house/ Vendor's Name | Application | Summary | PIC | Date Live | Category
3 | 2020-02-01 | 2020-02-01 | Perubahan Nama Aplikasi Maybank ID | BRD Done | Live | 2.9 | SR New - Penyesuaian Nama dan Icon New M2U | SR/0078/20 | Improvement | In-house | M2U Apps |  | Adon |  | Enhancement
1 | 2020-02-01 | 2020-02-01 | OJK scope: - Delete upload NPWP, signature, - Add liveness Dukcapil scope: - tambah field di screen agama dan warga negara - add field untuk simpan nama ibu balikan dukcapil - additional mapping Nama Ibu, Nama Ayah, No KK | BRD Done | Live | 2.9 |  | SR/0085/20 | Improvement | In-house | New M2U Apps |  | Adon |  | Regulatory
2 | 2020-02-01 | 2020-04-01 | Pembelian HCP (bancassurance) | BRD Done | Subjek Approval Regulator | 3.1 |  |  | New Feature | In-House | UIUX, …. |  | Chemi |  | Enhancement
1 | 2020-02-01 | 2020-03-01 | QRIS CPM UIUX | BRD Done | Live | 3.0 | SR QRIS CPM | SR/0151/20 | New Feature |  | UIUX |  | Adon |  | Regulatory
3 | 2020-02-01 | 2020-03-01 | Switch Console SMS Gateway M2U | BRD Done | Prod Prep (8 Apr 2020 - memo urgent) | 3.0 | BRD - Switch SMS Gateway | SR/0108/20 |  |  | ESB |  | Adon |  | Enhancement
1 | 2020-04-01 | 2020-05-01 | Masking Nomor Kartu ATM | BRD finalization | Hold based on email 31 Mar 2020 by Vebi | 3.1 | [8 empty] | Fraud
1 | 2020-03-01 | 2020-03-01 | NTB - MBM Feedback (Incomplete GCIF - M2U Apps) | BRD Done | Live | 3.0 | SR New - Perbaikan NTB | SR/0085/20 | Pending Item |  | UIUX |  | Adon |  | Regulatory
|  |  | NTB - MBM Feedback (Incomplete GCIF - impacted DCIF) | BRD Done | Pending Resource availability DCIF
|  |  | NTB - MBM Feedback | BRD Done | Pending Resource availability & FSD finalization
1 | 2020-03-01 | 2020-03-01 | QRPay Bit 51 MID Nasional | BRD finalization | Live | 3.0 | SR New - QRPay Bit 51 MID Nasional |  | Improvement | In-house | UIUX |  | Adon |  | Regulatory
1 | 2020-03-01 | 2020-05-01 | Pembelian Travel Insurance (bancassurance) | BRD finalization | Prod Prep (pending SR submission) |  |  |  | New Feature | In-House | UIUX, …. |  | Chemi |  | Enhancement
1 | 2020-03-01 | 2020-04-01 | Notifikasi Email Login dan Update Email PLN | BRD Finalization | FPPB on-going | 3.1 |  | SR/0065/20 | [6 empty] | Fraud
1 | 2020-03-01 | 2020-05-01 | Medallion - Mutual Fund | BRD Done | UAT |  |  |  | New Feature | In-House Medallion | UIUX, Medallion |  | Chemi |  | Enhancement
1 | 2020-03-01 | 2020-03-01 | Membership | BRD Done | Prod Prep (hide menu) | 3.0 | BRD - Membership_v1 | SR/0157/20 | New Feature |  | UIUX |  | Adon |  | Enhancement
2 | 2020-03-01 | 2020-03-01 | Register M2U After ATM Card Activation (register H+0) | BRD finalization | Prod Prep (Deploy 6 Apr 2020) | 3.0 | [8 empty] | Enhancement
2 | 2020-03-01 | 2020-03-01 | Embos NTB ATM Card (CPC) | BRD Done | Ready for UAT | 3.0 | SR New - NTB - Enhancement CPC | [7 empty] | Enhancement
3 | 2020-05-01 | 2020-06-01 | Penyesuaian TD Online | BRD finalization | FSD Finalization | 3.1 | SR New - TD Online | [5 empty] | Adon |  | Enhancement
2 | 2020-03-01 | 2020-03-01 | Penyesuaian Button di Iphone 11 | Perbaikan | Live | 3.0
2 | 2020-03-01 | 2020-04-01 | Perbaikan ETB : - Penambahan mapping kode cabang untuk rekening yang dibentuk dari cabang yang sudah ditutup - pengisian kode cabang dan NPK Sales pada layar IM2A untuk pembukaan rekening ETB - Penghapusan Rekening saldo 0 / NTB Dormant - Perbaikan Wording informasi TD Online Syariah | BRD finalization | SR Finalization | 3.1 |  |  | Improvement |  |  |  | Vebi |  | Enhancement
2 | 2020-03-01 | 2020-04-01 | Marketing Attribution | BRD finalization | Tender | 3.1
3 | 2020-03-01 | 2020-04-01 | Enhancement UIUX 3 : - Simplify Unlock & Forgot Password Process - Paket Data XL, 3, Indosat (+ M2U Web) - Digital Lifestyle Telkomsel (+M2U Web) | BRD finalization |  | 3.1 | [5 empty] | Prioritas Paket Data untuk UIUX | Adon |  | Enhancement
3 | 2020-04-01 | 2020-05-01 | FTL with responsive screen for BAOS | BRD finalization | Pending Resource availability | 3.1 | Tomy |  | Improvement | In-house | M2U, BAOS |  | Vebi |  | Enhancement
3 | 2020-04-01 | 2020-05-01 | Bulk account opening system (BAOS) | BRD finalization | FSD Finalization based in change request | 3.1 | OKI |  | New Feature | In-house | DCIF, BAOS |  | Vebi |  | Enhancement
3 | 2020-04-01 | 2020-05-01 | Reset PIN Credit Card | BRD finalization | Pending Resource availability |  | Depend on cardlink |  |  |  | UIUX |  | Christian Lesmana |  | Enhancement
2 | 2020-04-01 | 2020-05-01 | Digital Credit Card ETB | BRD finalization | to start FSD Finalization |  | BRD - Digital Credit Card Full Signed |  | New Feature |  |  |  | Christian |  | Enhancement
1 | 2020-04-01 | 2020-05-01 | Digital Branch : NTB (full KYC branch) ETB (link ATM card) Booking withdrawal | BRD finalization | [8 empty] | Vebi |  | Enhancement
1 | 2020-05-01 | 2020-06-01 | TAC by WA | BRD finalization | Tender |  | BRD - TAC by Whatsapp |  | New Feature |  |  |  | Chemi |  | Strategic
1 | 2020-05-01 | 2020-06-01 | Pengembangan Break Deposito & MyPlan | Pending BRD |  |  |  |  | Improvement | [5 empty] | Enhancement
1 | 2020-04-01 | 2020-05-01 | Transfer swift | BRD finalization | bagian dari proyek Digital Branch |  |  |  | New Feature |  |  |  | Christian |  | Enhancement
2 | 2020-05-01 | 2020-06-01 | Kredit Kepemilikan Mobil Fase 2 | Pending BRD |  |  |  |  | New Feature |  |  |  | Christian |  | Enhancement
2 | 2020-05-01 | 2020-06-01 | API management | BRD Done | Subjek Approval Regulator |  | BRD - API Management |  | New Feature | In-House | API Management |  | Christian |  | Enhancement
|  |  | SMS ATM Card activation for all account opening | BRD finalization
|  |  | eSignature | BRD finalization
1 | 2020-07-01 | 2020-08-01 | eMoney | BRD finalization | Prep Tender |  |  |  | New Feature |  |  |  | Adon |  | Strategic
|  |  | TAC Multi Channel Provider | Pending BRD | [10 empty] | Enhancement
|  |  | Case Status UID M2U Nasabah Unlock/Enable | BRD finalization |  |  | BRD - Penyesuaian Proses Reset Password dan Unlock v1.0 |  |  |  | M2U Apps |  | Adon |  | Bugs
|  |  | RTGS 4 field | Only M2U Web | Cancel |  |  |  | Improvement | In-House | UIUX |  | Adon |  | Regulatory
|  |  | link ke ASLI |  | Defer | [7 empty] | Vebi |  | Enhancement
|  |  | Update Pembelian ORI, Manajemen Kartu, Customer Care, T&C Biometric dan Limit QR Pada UIUX | Done | Done |  |  |  | Improvement | In-House | New M2U Apps |  | Adon | 2019-12-19 | Enhancement
|  |  | Fitur show dan hide balance, fitur service notif, pencarian nama bank tujuan dan penyesuaian nama produk | Done | Done |  |  |  | Improvement | In-House | New M2U Apps |  | Adon | 2019-12-19 | Enhancement
|  |  | Top Up E-Money Isaku | Done | Done |  |  |  | Improvement | In-House | New M2U Apps |  | Adon | 2019-12-19 | Enhancement
|  |  | QR Merchant On-boarding (eform) | Done | Done |  |  |  | New Feature |  |  |  | Vebi | 2019-11-01 | Enhancement
|  |  | Kredit Kepemilikan Mobil Fase 1 | Done | Done |  |  |  | New Feature |  |  |  | Christian | 2019-12-19 | Enhancement
|  |  | Pengembangan Activation dormant account | Done | Done |  |  |  | New Feature | Penril | M2U Web |  |  | 2019-11-01 | Enhancement
|  |  | Penambahan field SKN | Done | Done |  |  |  | New Feature | Penril | M2U Web |  | Adon | 2019-12-19 | Regulatory
|  |  | Pengembangan penambahan Admin Bank untuk XL prepaid | Done | Done |  |  |  | New Feature | Penril | M2U Web |  | Adon | 2019-12-19 | Enhancement
|  |  | Pengembangan penambahan Admin Bank untuk indosat prepaid | Done | Done |  |  |  | New Feature | Penril | M2U Web |  | Adon | 2019-12-19 | Enhancement
|  |  | Allianz Utama-RumahKu | Pending BRD |  |  |  |  | New Feature |  |  |  | Chemi |  | Enhancement
|  |  | Tokopedia Salam | BRD finalization |  |  |  |  | New Feature |  |  |  | Vebi |  | Enhancement
|  |  | Web Monitoring Backoffice NTB | BRD finalization |  |  |  |  | Improvement |  |  |  | Vebi |  | Enhancement
|  |  | Secure2U | [5 empty] | New Feature | [5 empty] | Strategic
|  |  | Apply loan SME | Pending BRD |  |  |  |  | New Feature |  |  |  | Christian |  | Enhancement
|  |  | QR Upload (yg kyk gopay dr merchant gramed) | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Daftar M2U non kartu ATM | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Menampilkan join acc di uiux dan Tampilan Rekening QQ jika bertransaksi di UIUX | ?? |  |  |  |  | Improvement | In-house |  |  | Adon |  | Enhancement
|  |  | QR Merchant On-boarding (eform) - integration | Pending BRD |  |  |  |  | Improvement |  |  |  | Vebi |  | Enhancement
|  |  | Auto Purge for Existing to Bank Account (0 Balance) | BRD finalization |  |  |  |  | Improvement |  |  |  | Vebi |  | Enhancement
|  |  | Aktivasi Dormant NTB dengan KYC Video Call | Pending BRD |  |  |  |  | Improvement | [5 empty] | Enhancement
|  |  | Maybank Gift | Pending BRD |  |  |  |  | New Feature |  |  |  | Chemi |  | Enhancement
|  |  | PFM | Pending BRD |  |  |  |  | New Feature |  |  |  | Chemi |  | Enhancement
|  |  | Gamification | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Change PIN ATM | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Personalize Promo | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Ganti User ID | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Ganti No HP M2U | Pending BRD |  |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | ATM Direct Marketing | IT SC | Drop |  |  |  | New Feature | [5 empty] | Enhancement
|  |  | Pengembangan M2U mengirimkan no kartu debit real | Pending BRD Update |  |  |  |  | New Feature | Penril | M2U Web |  |  |  | Enhancement
|  |  | Pengembangan MSS untuk secure email | Development Prep |  |  |  |  | New Feature | Penril | M2U Web |  |  |  | Enhancement
|  |  | Pengembangan Account summary | Development Prep |  |  |  |  | New Feature | Penril | M2U Web |  | Adon |  | Enhancement
|  |  | Remove Rate Convertion & Expiry Date Inquiry from ESB | UAT M2E |  |  |  |  | New Feature | Penril | M2U Web |  |  |  | Enhancement
|  |  | Pengembangan transaction fall back master card | Development Prep |  |  |  |  | New Feature | Diebold | PCE |  |  |  | Enhancement
|  |  | Pengembangan automatic pengiriman journal ATM ke PCE dan systematic | Development Prep |  |  |  |  | New Feature | Diebold | PCE |  |  |  | Enhancement
|  |  | Pengembanan reversal rintis | Development Prep |  |  |  |  | New Feature | Diebold | PCE |  |  |  | Enhancement
|  |  | PIN change dari M2U | Development Prep |  |  |  |  | New Feature | Diebold | PCE |  |  |  | Enhancement
|  |  | Pengembangan Line payment | Pending Effort |  |  |  |  | New Feature | Diebold | PCE |  |  |  | Enhancement
|  |  | FX Pricing | Pending BRD |  |  |  |  | Improvement | Penril, In-House | M2U Web, New M2U Apps |  |  |  | Enhancement
|  |  | Diaspora Bonds | Pending BRD |  |  |  |  | New Feature | … | … |  |  |  | Enhancement
|  |  | QR Cashback Realtime | Pending BRD | [10 empty] | Enhancement
|  |  | QR Merchant App | Pending BRD | [8 empty] | Christian |  | Enhancement
|  |  | Notifikasi Nasabah Login Beda Device, Browser, HP | Pending BRD |  |  |  |  | New Feature |  |  |  | Adon |  | Fraud
|  |  | Default NPWP jika di Skip isinya 0000 | Pending BRD
|  |  | Perubahan Product Code NTB Maksi2u | Pending BRD | [10 empty] | Enhancement
|  |  | QR Merchant On-boarding (eform) Phase 1.5 | Pending BRD | [10 empty] | Enhancement
|  |  | Digital Credit Card NTB | Pending BRD | [10 empty] | Enhancement
Strategic